## Gantt Chart
PROJECT TITLE |  | Lofthus Frukt og Saft |  |  |  |  | COMPANY NAME | [6 empty] | Gry Aina's web development team
PROJECT MANAGER |  | Gry Aina Lauritsen |  |  |  |  | DATE | [6 empty] | 2019-04-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Start and Planning
1.1 | Client meeting | Project Manager | 2019-04-01 | 2019-04-02 | 1 | 0% | bar: WEEK 1 M; WEEK 2 W to WEEK 2 F
1.2 | Kickoff meeting | Project Manager Content Developer Designer Copywriter Frond-end Developer Back-end Developer | 2019-04-01 | 2019-04-02 | 1 | 0% | bar: WEEK 1 M; WEEK 2 W to WEEK 2 F
1.3 | Project planning/Organize team on Slack | Project Manager | 2019-04-02 | 2019-04-03 | 1 | 0% | bar: WEEK 1 T; WEEK 2 W to WEEK 2 F
1.4 | Verifying staff meeting | Project Manager Content Developer Designer Copywriter Frond-end Developer Back-end Developer | 2019-04-02 | 2019-04-03 | 1 | 0% | bar: WEEK 1 T; WEEK 2 W to WEEK 2 F
1.5 | Meeting with photographer | Project Manager Photographer | 2019-04-03 | 2019-04-04 | 1 | 0% | bar: WEEK 1 W; WEEK 2 W to WEEK 2 F
1.6 | Project management and client contact | Project Manager | 2019-04-03 | 2019-05-03 | 23 | 0% | bar: WEEK 1 W to WEEK 5 F
2 | Project Research
2.1 | Analyzing company, brand strategy and recognizing target group | Content Developer Designer | 2019-04-02 | 2019-04-04 | 2 | 0% | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W to WEEK 2 F
2.2 | Research competitor brands | Content Developer Designer | 2019-04-04 | 2019-04-05 | 1 | 0% | bar: WEEK 1 T; WEEK 2 W to WEEK 2 F
2.3 | Make wireframe | Designer | 2019-04-05 | 2019-04-06 | 1 | 0% | bar: WEEK 1 F; WEEK 2 W to WEEK 2 F
4 | Design and Content
4.1 | Planning content | Content Developer Designer Copywriter Photographer | 2019-04-08 | 2019-04-10 | 2 | 0%
4.2 | Making moodboard and style tiles | Designer | 2019-04-10 | 2019-04-12 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F
4.3 | Creating written content | Copywriter | 2019-04-10 | 2019-04-13 | 3 | 0% | bar: WEEK 2 W to WEEK 2 F
4.4 | Photographing in Hardanger | Photographer | 2019-04-10 | 2019-04-13 | 3 | 0% | bar: WEEK 2 W to WEEK 2 F
4.5 | Create mockup | Designer | 2019-04-10 | 2019-04-12 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F
5 | Site Building
5.1 | HTML and CSS | Front-end Developer | 2019-04-12 | 2019-04-19 | 5 | 0% | bar: WEEK 2 W to WEEK 3 T
5.2 | Javascript | Front-end Developer | 2019-04-19 | 2019-04-26 | 6 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F to WEEK 4 F
5.3 | Building database | Back-end Developer | 2019-04-19 | 2019-04-26 | 6 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F to WEEK 4 F
6 | Finalizing and bug testing
6.1 | Cross platform and browser testing | Front-end Developer | 2019-04-29 | 2019-05-01 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 5 T
6.2 | Quality and accessibility testing | Quality Assurance Engineer | 2019-04-30 | 2019-05-02 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 T to WEEK 5 W
6.3 | Refinement | Front-end Developer | 2019-05-02 | 2019-05-03 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 T
6.4 | Launch | Project Manager Content Developer Designer Front-end developer Back-end developer | 2019-05-03 | 2019-05-04 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 5 F